## WBS
Function/Screen | Feature | Sub Feature | Type | Function/Screen Description | Level* | Requirement | Design | Coding | Test | Deploy | Planned | Status | SRS | In-Charge | Deadline | IT Case | Author
User Registration Screen | Authentication | UC-AUTH-01 | Screen | Register Consumer or Farmer Account | Simple | 1 | 0.9 | 1.8 | 0.7 | 0.3 | Iteration 1 | To Do | Done |  |  | To Do | Dự
Profile & Farm Management Screen | Authentication | UC-AUTH-03 | Screen | Complete and Manage Profile | Medium | 1 | 1.2 | 3.4 | 1.2 | 0.5 | Iteration 1 | To Do | Done |  |  | To Do | Dự
Sign In Screen | Authentication | UC-AUTH-04 | Screen | Log In | Simple | 1 | 0.9 | 1.8 | 0.7 | 0.3 | Iteration 1 | To Do | Done |  |  | To Do | Tú
Logout Handler | Authentication | UC-AUTH-05 | Function | Log Out | Simple | 1 | 0.9 | 1.8 | 0.7 | 0.3 | Iteration 1 | To Do | Done |  |  | To Do | Tú
Change Password Screen | Authentication | UC-AUTH-06 | Screen | Change Password | Simple | 1 | 0.9 | 1.8 | 0.7 | 0.3 | Iteration 1 | To Do | Done |  |  | To Do | Thương
Agricultural Marketplace Screen | Marketplace | UC-MKT-01 | Screen | Browse and Search Marketplace | Medium | 1 | 1.2 | 3.8 | 1.4 | 0.6 | Iteration 1 | To Do | Done |  |  | To Do | Thương
Product Detail & Batches Screen | Marketplace | UC-MKT-02 | Screen | View Product Detail | Medium | 1 | 1.2 | 3.8 | 1.4 | 0.6 | Iteration 1 | To Do | Done |  |  | To Do | Thương
Farmer Product Management Screen | Product Management | UC-FAR-03 | Screen | Manage Product Listing | Medium | 1 | 1.2 | 4.3 | 1.6 | 0.6 | Iteration 1 | To Do | Done |  |  | To Do | Lò Mạnh Xum
User Management Screen | Administration | UC-ADM-03 | Screen | Manage User Account Status | Simple | 1 | 0.9 | 2.2 | 0.8 | 0.3 | Iteration 1 | To Do | Done |  |  | To Do | Huy
Product Categories Management Screen | Administration | UC-ADM-05 | Screen | Manage Product Categories | Simple | 1 | 0.9 | 1.8 | 0.6 | 0.3 | Iteration 1 | To Do | Done |  |  | To Do | Huy
Shopping Cart Screen | Consumer Ordering | UC-CON-01 | Screen | Manage Shopping Cart | Simple | 1 | 0.9 | 1.8 | 0.6 | 0.3 | Iteration 1 | To Do | Done |  |  | To Do | Lò Mạnh Xum
Retail Checkout Screen | Consumer Ordering | UC-CON-02 | Screen | Checkout and Place Retail Order | Complex | 1 | 1.5 | 8.1 | 3.1 | 1.2 | Iteration 1 | To Do | Done |  |  | To Do | Huy
Order Tracking & History Screen | Consumer Ordering | UC-CON-04 | Screen | Track Retail Order | Medium | 1 | 1.2 | 2.9 | 1.1 | 0.4 | Iteration 1 | To Do | Done |  |  | To Do | Dự
Farmer Order Fulfillment Screen | Farmer Sales | UC-FAR-06 | Screen | Process Order | Medium | 1 | 1.1 | 3.4 | 1.2 | 0.5 | Iteration 1 | To Do | Done |  |  | To Do | Lò Mạnh Xum
Product Listing Moderation Screen | Administration | UC-ADM-04 | Screen | Moderate Product Listing | Medium | 1 | 1.1 | 3.3 | 1.2 | 0.5 | Iteration 1 | To Do | Done |  |  | To Do | Tú
Forgot & Reset Password Screen | Authentication | UC-AUTH-07 | Screen | Reset Password | Medium | 1 | 1 | 3.6 | 1.2 | 0.7 | Iteration 2 | To Do | Done |  |  | To Do | Huy
Product Origin & Farming Log Screen | Traceability | UC-TRC-01 | Screen | View Product Traceability | Medium | 1 | 1 | 3.1 | 1 | 0.6 | Iteration 2 | To Do | To Do |  |  | To Do
Crop Season Management Screen | Farm Management | UC-FAR-01 | Screen | Manage Farm and Crop Seasons | Medium | 1 | 1 | 3.6 | 1.2 | 0.7 | Iteration 2 | To Do | To Do |  |  | To Do
Digital Field Log Screen | Farm Management | UC-FAR-02 | Screen | Record E-Farming Logs | Medium | 1 | 1 | 3.1 | 1 | 0.6 | Iteration 2 | To Do | To Do |  |  | To Do
Batch & Traceability QR Generator Screen | Product Traceability | UC-FAR-04 | Screen | Manage Product Batch and Traceability | Complex | 1 | 1.2 | 6.4 | 2.2 | 1.4 | Iteration 2 | To Do | To Do |  |  | To Do
Seller & Buyer KYC Review Screen | Administration | UC-ADM-02 | Screen | Approve or Reject KYC Account | Medium | 1 | 1 | 3.1 | 1 | 0.6 | Iteration 2 | To Do | To Do |  |  | To Do
QR Payment & Transfer Screen | Consumer Payment | UC-CON-03 | Screen | Pay Retail Order by VietQR or PayOS | Complex | 1 | 1.2 | 6.4 | 2.2 | 1.4 | Iteration 2 | To Do | To Do |  |  | To Do
Product Review Modal | Consumer Engagement | UC-CON-05 | Screen | Submit Product Review | Simple | 1 | 0.7 | 1.7 | 0.6 | 0.4 | Iteration 2 | To Do | To Do |  |  | To Do
Order Dispute & Complaint Screen | Consumer Engagement | UC-CON-06 | Screen | Submit Order Complaint | Medium | 1 | 1 | 3.1 | 1 | 0.6 | Iteration 2 | To Do | To Do |  |  | To Do
Complaint Arbitration & Refund Screen | Administration | UC-ADM-06 | Screen | Resolve Complaint | Complex | 1 | 1.2 | 6.4 | 2.2 | 1.4 | Iteration 2 | To Do | To Do |  |  | To Do
Review Moderation Screen | Administration | UC-ADM-08 | Screen | Moderate Product Review | Simple | 1 | 0.7 | 1.7 | 0.5 | 0.4 | Iteration 2 | To Do | To Do |  |  | To Do
Certification Verification Dossier Screen | Certification | UC-FAR-07 | Screen | Submit Certificate Dossier | Medium | 1 | 1 | 2.7 | 0.9 | 0.6 | Iteration 2 | To Do | To Do |  |  | To Do
Platform Promotion & Voucher Screen | Administration | UC-ADM-07 | Screen | Manage Promotions and Vouchers | Medium | 1 | 1 | 3.1 | 1 | 0.6 | Iteration 2 | To Do | To Do |  |  | To Do
B2B Registration Screen | Authentication | UC-AUTH-02 | Screen | Register Buyer B2B Account | Medium | 1 | 0.9 | 1.7 | 1.1 | 0.7 | Iteration 3 | To Do | To Do |  |  | To Do
Admin Master Dashboard Screen | Administration | UC-ADM-01 | Screen | View Platform Dashboard and Pending Work | Complex | 1 | 1.2 | 2.7 | 1.8 | 1.1 | Iteration 3 | To Do | To Do |  |  | To Do
B2B Supplier Directory Screen | B2B Procurement | UC-B2B-01 | Screen | Search Suppliers and Production Regions | Medium | 1 | 0.9 | 1.7 | 1.1 | 0.7 | Iteration 3 | To Do | To Do |  |  | To Do
Farm Capacity & Credibility Screen | B2B Procurement | UC-B2B-02 | Screen | View Supplier Capacity Profile | Medium | 1 | 0.9 | 1.5 | 1 | 0.6 | Iteration 3 | To Do | To Do |  |  | To Do
Wholesale Order Creation Screen | B2B Procurement | UC-B2B-03 | Screen | Create Wholesale Order | Complex | 1 | 1.2 | 3 | 2.1 | 1.2 | Iteration 3 | To Do | To Do |  |  | To Do
Seasonal Pre-Order Setup Screen | B2B Procurement | UC-B2B-04 | Screen | Create Pre-Order Commitment | Complex | 1 | 1.1 | 3 | 2.1 | 1.2 | Iteration 3 | To Do | To Do |  |  | To Do
Pre-Order Campaign Management Screen | Farmer Sales | UC-FAR-05 | Screen | Manage Pre-Order Campaign | Medium | 1 | 0.9 | 1.7 | 1.1 | 0.7 | Iteration 3 | To Do | To Do |  |  | To Do
Offtake Contract Drafting Screen | B2B Contract Management | UC-B2B-05 | Screen | Create Offtake Contract Proposal | Complex | 1 | 1.1 | 2.7 | 1.8 | 1.1 | Iteration 3 | To Do | To Do |  |  | To Do
Digital Contract Signing Screen | B2B Contract Management | UC-B2B-06 | Screen | Sign Offtake Contract | Medium | 1 | 0.9 | 1.7 | 1.1 | 0.7 | Iteration 3 | To Do | To Do |  |  | To Do
B2B Contract Milestone Tracking Screen | B2B Contract Management | UC-B2B-07 | Screen | Track B2B Order and Contract Progress | Complex | 1 | 1.1 | 2.7 | 1.8 | 1.1 | Iteration 3 | To Do | To Do |  |  | To Do
B2B Membership Plans Screen | B2B Membership | UC-B2B-08 | Screen | Manage Buyer Subscription | Medium | 1 | 0.9 | 1.7 | 1.1 | 0.6 | Iteration 3 | To Do | To Do |  |  | To Do
Farmer Offtake Contracts Screen | B2B Contract Management | UC-FAR-08 | Screen | Manage Offtake Contract | Medium | 1 | 0.9 | 1.7 | 1.1 | 0.6 | Iteration 3 | To Do | To Do |  |  | To Do
Farmer Revenue & Analytics Screen | Farmer Analytics | UC-FAR-09 | Screen | View Revenue and Cash-Flow Dashboard | Complex | 1 | 1.1 | 2.7 | 1.8 | 1.1 | Iteration 3 | To Do | To Do |  |  | To Do
B2B Subscription Tiers Screen | Administration | UC-ADM-09 | Screen | Manage Subscription Tiers | Medium | 1 | 0.9 | 1.5 | 1 | 0.6 | Iteration 3 | To Do | To Do |  |  | To Do
(*) You can rate the functions' complexity level based on the number of fields on the screens or the number of transactions in the function, with the details as below
Simple | <=7 fields | <=3 transactions
Medium | <=15 fields | <= 7 transactions |  |  |  | Planned | Functions | Requirement | Design | Coding | Test | Deploy | Total PDS
Complex | >15 fields | > 7 transactions |  |  |  | Iteration 1 | 15 | 15 | 16 | 46 | 17 | 7 | 101
In which: | [5 empty] | Iteration 2 | 13 | 13 | 13 | 48 | 16 | 10 | 100
fields: screen components or database table fields | [5 empty] | Iteration 3 | 14 | 14 | 14 | 30 | 20 | 12 | 90
transactions can be counted actioning UI components, user or database access transactions | [5 empty] | Grand Total | 42 | 42 | 43 | 124 | 53 | 29 | 291

## Q&A
Date | Question | By | Priority | Due Date | Status | Note (answer, other notes)
2023-09-16 |  | KienNT | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open

## Issues
Date | Issue | Priority | Created | Owner | Due Date | Status | Notes
2024-10-13 |  | Medium | KienNT | HuyNMG |  | Open
|  | Medium |  | HuyNMG |  | Open
|  | Medium |  | HuyNG |  | Open
|  | Medium |  | HuyNG |  | Open
|  | Medium |  | HuyNG |  | Open
|  | Medium |  | DucBH |  | Open
|  | Medium |  | HuyLQ |  | Open

## Defects
Date | Defect Description | Activity | Product | Product Details | Assigner | Assignee | Status | Updated | Notes
2024-10-13 |  | Review | Software Package |  |  |  | Pending | 2024-10-26
|  | Review | Report1 (Intro) |  |  |  | Pending
|  | Review | Report4 (SDS) |  |  |  | Pending
|  | Review | Report4 (SDS) |  |  |  | Pending
|  | Review | Report5 (Test) |  |  |  | Pending
|  | Review | Report6 (Guides) |  |  |  | Pending
|  | Review | Report4 (SDS) |  |  |  | Pending
|  | Review | Report4 (SDS) |  |  |  | Pending
|  | Review | Report5 (Test) |  |  |  | Pending
|  | Review | Report6 (Guides) |  |  |  | Pending
|  | Review | Software/System |  |  |  | Pending
|  | Review | Software/System |  |  |  | Pending